Sprint Plan 2

Module: COM435 – Software Product and Process Management
Project: Family Travel Companion
Sprint Duration: One Week (Tuesday – Monday)

1. Sprint Goal

Finalize a structured and academically compliant product backlog by:

- Completing 2 user stories (S4, S28) with acceptance criteria

- The team will collaboratively develop 2 spike stories:

  - 1 Technical spike

  - 1 Functional spike

- The remaining 6 spike stories will be completed individually by assigned team members.

- This approach ensures balanced contribution and addresses both technical and functional uncertainties effectively.

- Ensuring compliance with coursework template

2. Scrum Team

| Role | Assigned To |
| --- | --- |
| Product Owner | Habibur Rahman (B0100963) |
| Scrum Master | MD Ali Hasan Jidan (B01011849) |
| Development Team | MD Ali Hasan Jidan, Habibur Rahman, Md Jahirul Islam, Komalpreet Kaur, Sheheryar Khan, Syed Abdul Hafeez |

3. Sprint Objectives

- Complete Story-5 (S4) – Centralised booking

- Complete Story-6 (S28) – Points redemption

- Complete Spike 1 – Real-time sync

- Complete Spike 2 – Promotion rules

- Complete Spike 3 – Offline storage

- Complete Spike 4 – Scalable media storage

- Complete Spike 5 – AI recommendations

- Complete Spike 6 – Digital signatures

- Complete Spike 7 – Corporate verification

- Complete Spike 8 – Gamification rules

4. User Stories

Story-5 (S4) – Book accommodations, transport, activities

| Field | Value |
| --- | --- |
| Originator | Team |
| Story ID | S4 |
| Feature ID | F1 |
| Points | 8 |

Acceptance Criteria:

Happy Path: Successful booking with confirmations stored, calendar updated, notifications sent.

Unhappy Path: Payment failure clear error with retry/draft options.

Edge Case: Insufficient capacity alert with alternatives and waitlist.

Story-6 (S28) – Redeem points for rewards

| Field | Value |
| --- | --- |
| Originator | Team |
| Story ID | S28 |
| Feature ID | F8 |
| Points | 5 |

Acceptance Criteria:

Happy Path: Successful redemption points deducted, voucher created, dashboard updated.

Unhappy Path: Insufficient points message with links to earn more.

Edge Case: Points expiring soon warning and recommendations.

5. Spike Stories

| No | Title | Type | Owner | Days |
| --- | --- | --- | --- | --- |
| 1 | Real-Time Synchronisation | Technical | Team | 3 |
| 2 | Promotion Eligibility Rules | Functional | Team | 2 |
| 3 | Secure Offline Storage | Technical | MD Ali Hasan Jidan | 2 |
| 4 | Scalable Media Storage | Technical | Habibur Rahman | 2 |
| 5 | AI Recommendation Methods | Technical | Md Jahirul Islam | 2 |
| 6 | Digital Signature Technology | Technical | Komalpreet Kaur | 2 |
| 7 | Corporate Eligibility Verification | Technical | Sheheryar Khan | 2 |
| 8 | Gamification Rules | Functional | Syed Abdul Hafeez | 2 |

6. Sprint Schedule

| Day | Activities |
| --- | --- |
| Tuesday | Sprint Planning, assign stories and spikes |
| Wednesday | Begin Story-5, begin Spikes 1 & 2 |
| Thursday | Continue Story-5, continue Spikes 1 & 2 |
| Friday | Begin Story-6, begin Spikes 3, 4, 5 |
| Saturday | Complete Story-5 testing, continue Spikes 3–7 |
| Sunday | Complete Story-6 testing, complete Spikes 1 & 2 reports |
| Monday | Finalize all spikes, team review, prepare report |

7. Daily Scrum (15 mins each morning)

- What did I complete yesterday?

- What will I work on today?

- Any blockers?

8. Definition of Done

For User Stories:

- All acceptance criteria tested and passing.

- Documentation updated.

- No critical bugs.

For Spike Stories:

- Completed within time-box.

- Findings report with recommendation.

- Shared with team.

9. Risk Assessment

| Risk | Mitigation |
| --- | --- |
| Real-time sync complexity | Spike produces recommendation; defer if needed |
| Payment integration delays | Use sandbox early; fallback options |
| AI accuracy concerns | Spike evaluates multiple approaches |
| Digital signature legality | Research requirements |
| Team availability | Clear ownership; daily stand-ups |

10. Approval

| Role | Name | Date |
| --- | --- | --- |
| Product Owner | Habibur Rahman (B0100963) | 09/03/2026 |
| Scrum Master | MD Ali Hasan Jidan (B01011849) | 09/03/2026 |
| Development Team | All Members | 09/03/2026 |